## PROJECT
PROJECT TITLE: |  | Medical specialist’s appointment system
MAIN OBJECTIVE: |  | To develop medical specialist’s appointment system that will allow patients to make appointment to the particular specialist of his/her problem
SPECIFIC OBJECTIVES:
| 1 | To gather and analyze requirements
| 2 | To design user interface and database
| 3 | To implement database
| 4 | To develop a web-based application
Identify the stakeholders in your project
| 1 | System developer
| 2 | Patients
| 3 | project team
| 4 | Doctors
5

## DELIVERABLES
S/N. | GOAL/OBJECTIVE | DELIVERABLE(S) | Estimated Delivery Date
1 | To gather and analyze requirements | Requirement definition | 12 days
2 | To design user interface | User interface | 7 day
3 | To design database | Entity relationship diagram | 2 Weeks
4 | To develop a web-based application | New system | 2 Weeks

## TASKS
S/N. | TASK | LEAD | DURATION(days) | DEPENDENCIES
1 | To identify project business benefits | Ibrahim | 3
2 | To identify project objectives |  | 4
2.1 | To identify main objectives |  | 3
2.2 | To identify specific objectives |  | 1 | T2.1
3 | To select requirement gathering techniques (questionnaire and observation) | Ibrahim | 14
3.1 | Sampling of stakeholders for questionnaire |  | 2
3.2 | Making appointment for questionnaire |  | 2 | T3.1
3.3 | Preparation of questions for questionnaire |  | 1
3.4 | Conducting questionnaire |  | 2 | T3.1,3.2,3.3
3.5 | Observation for manual system |  | 1
3.6 | Documenting collected informations |  | 2 | T3.4,3.5
3.7 | To identify system requirements |  | 2 | T3.6
3.7.1 | To identify functional requirements |  | 1
3.7.2 | To identify non- functional requirements |  | 1
3.8 | To create requirement definition document |  | 2 | T3.7.1,3.7.2
4 | System design | Baruani | 20 | T3.7
4.1 | Database design |  | 5 | T3.8
4.1.1 | To draw ERD |  | 1
4.1.2 | To perform normalization |  | 2 | T4.1.1
4.1.3 | To create relational schemas |  | 1 | T4.1.2
4.1.4 | To choose DBMS |  | 1
4.2 | User interface design | Emaculate | 5
4.2.1 | To design layout (font, color) |  | 2
4.2.2 | To design navigation (buttons, menus, links) |  | 3
4.3 | Architecture design |  | 5
4.3.1 | To identify hardwares that system will run (PC, tablet, smartphone) |  | 2
4.3.2 | To identify softwares that system will run |  | 3
(all browsers, different OS like windows, macOS and linux)
4.4 | Program design | Octav | 5
4.4.1 | To draw DFD and context diagram |  | 3
4.4.2 | To draw use case |  | 2
5 | System implementation | Rose | 12 | T4
5.1 | Coding |  | 5
5.2 | Unit testing |  | 2 | T5.1
5.3 | Debugging |  | 2 | T5.2
5.4 | System integration |  | 1
5.5 | System testing |  | 2 | T5.4

## REQUIREMENTS
S/N | Detailed Requirements | Category
Functional requirement
1 | System should allow administrator to register patients and doctors | Evident
2 | System should allow users (administrator, patients and doctors) to login | Evident
3 | System should allow patient to make appointment for specialist | Evident
4 | System should display number of patients that has made appointment to the specialist | Evident
5 | System should display number of allowed appointments for each doctor | Evident
6 | System should avoid more appointments when the doctor is full occupied | Hidden
7 | System should allow specialist doctors to view appointment | Evident
8 | System should allow searching different items | Evident
9 | System should allow users to reset password | Evident
Non functional requirement
10 | System should be responsive to different devices
11 | System should be available for use 24 hours per day
12 | System should allow encryption of sensitive data like passwords

## GANTTCHART
Software Engineering Group 13 Project Schedule
| Project Start Date | 2021-01-04 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | GROUP 13 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22
 | time axis 2021-01-04 to 2021-02-28
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2021-01-04 to 2021-02-28
1 | To identify project business benefits | Ibrahim |  |  |  | 3
2 | To identify project objectives |  |  |  |  | 4
2.1 | To identify main objectives |  |  |  |  | 3
2.2 | To identify specific objectives |  |  |  |  | 1
3 | To select requirement gathering techniques | Ibrahim |  |  |  | 14
(questionnaire and observation)
3.1 | Sampling of stakeholders for questionnaire |  |  |  |  | 2
3.2 | Making appointment for questionnaire |  |  |  |  | 2
3.3 | Preparation of questions for questionnaire |  |  |  |  | 1
3.4 | Conducting questionnaire |  |  |  |  | 2
3.5 | Observation for manual system |  |  |  |  | 1
3.6 | Documenting collected informations |  |  |  |  | 2
3.7 | To identify system requirements |  |  |  |  | 2
3.7.1 | To identify functional requirements |  |  |  |  | 1
3.7.2 | To identify non- functional requirements |  |  |  |  | 1
3.8 | To create requirement definition document |  |  |  |  | 2
4 | System design | Baruani |  |  |  | 20
4.1 | Database design |  |  |  |  | 5
4.1.1 | To draw ERD |  |  |  |  | 1
4.1.2 | To perform normalization |  |  |  |  | 2
4.1.3 | To create relational schemas |  |  |  |  | 1
4.1.4 | To choose DBMS |  |  |  |  | 1
4.2 | User interface design | Emaculate |  |  |  | 5
4.2.1 | To design layout (font, color) |  |  |  |  | 2
4.2.2 | To design navigation (buttons, menus, links) |  |  |  |  | 3
4.3 | Architecture design |  |  |  |  | 5
4.3.1 | To identify hardwares that system will run (PC, tablet, smartphone) |  |  |  |  | 2
4.3.2 | To identify softwares that system will run |  |  |  |  | 3
(all browsers, different OS like windows, macOS and linux)
4.4 | Program design | Octav |  |  |  | 5
4.4.1 | To draw DFD and context diagram |  |  |  |  | 3
4.4.2 | To draw use case |  |  |  |  | 2
5 | System implementation | Rose |  |  |  | 12
5.1 | Coding |  |  |  |  | 5
5.2 | Unit testing |  |  |  |  | 2
5.3 | Debugging |  |  |  |  | 2
5.4 | System integration |  |  |  |  | 1
5.5 | System testing |  |  |  |  | 2
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## CONSTRAINTS
S/N. | PROJECT CONSTRAINTS
1 | Unexpected budget cuts
2 | Shortage of time to complete the project
3 | Poor cooperation and response from Stakeholders
4 | Weather problems while gathering requirements

## RISK MANAGEMENT
S/N. | RISK | CATEGORY | PROBABILITY | EFFECT | WHAT WILL YOU DO IF IT HAPPENS |  | WHAT WILL YOU DO TO MITIGATE IT (PREVENT IT FROM HAPPENING)
1 | Cost, unexpected budget cuts | Project and product risk | Low | Serious | 1 | Compansate the cost exceeded | 1 | Add extra budget for the case of emergency
2 | Time, shortage of time | Project, Project and Business | High | Serious | 1 | Working overtime and holidays | 1 | Proper tasks division
3 | Poor response from Stakeholders | Project risk and Product | Moderate | Serious | 1 | To choose for another altenative stakeholder | 1 | Having altenative stakeholders
4 | Weather problems | Project | Low | Low | 1 | Working remotely | 1 | Prepare enviroment to work from a remote area
5 | Requirements change | Project risk and Product | Low | Catastrophic | 1 | Change methodology to Iterative | 1 | Use Waterfall methodology
6 | Technology change | Business risk | Low | Serious | 1 | Outsource the project | 1 | Train professionals to cope with new technologies

## BUDGET
S/N | COST
1 | Buying internet bundles
2 | Transportation cost for seeking requirement
3 | Printing reports